## Sheet1
Date | Collaborator | Main task | Subtask
2024-10-30 | Ruth | Setting up enviroment | creating a new repo
creating an index file
Imprting neccesary files
Business understanding
| John & Cess |  | Come up with a clear business undertanding
Use refereference where posible
Ruth and Joseline

## Sheet2
ANEMIA LEVEL IN CHILREN
Name | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11
Heading |  | Business understanding and Objective | Data Loading,inspection data dictionary Insights | Data preparation |  | EDA | Prepocessing | No meeting: Build the models and come upwith coclusions and recommedations | Modelling |  | Deployment |  | Final report | Team approval
All | 2024-10-30: Clear defined objectives; 2024-10-31: all team mebers to load, inspect and draw insights; 2024-11-01: all team mebers to take part in data clening; 2024-11-03: Come up with different EDA and draw insights; 2024-11-04: Preprocessing, give the team reason why you have opted for that technique; 2024-11-06: Presentation of different models; 2024-11-08: Model testing and deployment
Agatha | 2024-10-30: Working on limitation of the dataset. Provide reference of posible; 2024-11-10: Powerpoint preparation
John mbego | 2024-10-31: Define the dictionary( colums and their meaning)
Joseline | 2024-10-30: Define a clear problemt statement
Ruth | 2024-10-29: Setting up a working environment
Cecilia | 2024-10-30: Define a clear business understand with reference if posible
Leonard | 2024-11-10: Data Report